Viridian

To:	ECMB

From:	Kim Oswald, on Behalf of the ECMB Evaluation Committee

Date: 	September 9, 2008

RE:	Evaluation Committee Status Report – for September meeting

### Residential Studies

#### Demand and Energy Savings in Residential Lighting - Regional

The regional Evaluation Working Group is participating in a study of lighting products installed through Markdown programs.  Since most lighting going into homes both now and in the future is purchased through markdown programs at point of purchase, it is especially difficult to determine (1) who is buying (2) what products (3) installing them in what sockets, if any, and (4) using them for how many hours per day/year.  This study will develop an initial sample and recommend how program managers and/or evaluators might continue developing samples.  Then the study will determine energy savings and coincident demand savings for the lighting installed.   The NMR/RLW team provided a draft memo, outlining initial findings on the proportion of customer installations are cost-effective and estimating numbers of cost effective installations still remaining for future conversion.  That memo will become part of the final report.  This study is nearing completion.

CT added a component to the study examining purchasing motivation and behavior.  This portion was done using an in-person intercept at several “big box” stores.  Draft results of this portion of the study have been provided and are under review.

#### Measure Life and Persistence - Regional

The regional Evaluation Working Group is participating in a study of lighting products installed in coupon and direct install programs.  While these programs form a small and declining portion of the residential portfolio in Connecticut, the study is important for determining: (1) whether products remain in their original installed locations (2) product failure rates (3) product removal rates and (4) reasons for the remaining factors.

#### Ductless Heat Pumps: Energy and Demand Savings; Customer Satisfaction - Regional

This regional study is designed to assess results from the Ductless Split Heat Pump pilot programs offered in Massachusetts and Connecticut. NSTAR is managing the project.  RLW Analytics and Nexus Market Research are the contractors for this project, which was kicked-off on December 7, 2007.   The winter phase of the project was completed on schedule.  On March 11, NMR provided a draft interim report indicating the results of contractor and some customer interviews.   Additional homes were recruited to augment the winter sample with additional customers.  Summer season savings and customer satisfaction information have been collected over the summer using open ended surveys and interviews.  Focus groups have been completed to gain more in-depth information from participants.  Project completion was scheduled for this October soon after the end of the cooling season.  However, the contractor now indicates that difficulties scheduling meter removals and a complicated analysis may delay the final report until December.  RLW is providing weekly updates to the NSTAR project manager.

#### Residential Central Air Conditioning - Regional

The Residential CAC study will examine load shapes, coincidence factors and savings from various CAC measures.  This study will be done within the regional Evaluation Working Group.  During the first year of the study, the study will produce summer usage profiles for replacement air conditioners.  During the second year, if the Sponsors elect to add a second year, additional measures such as tune-ups, duct-sealing, and right-sizing will be examined.

ADM Associates was selected to complete the first year of the study with an option for Year 2.  There have been many delays to date.  ADM has just recently produced an acceptable workplan and budget; thus P.O.s are just being released now.  ADM is currently metering central air conditioners at customer premises.   This phase will be complete in October.

#### Home Energy Solutions Impact Evaluation - CT

This study will examine the impacts of measures installed in the HES program.  Because the broad range of services for which different customer groups are eligible greatly complicates the analysis, the study will focus primarily on measures or groups of measures with the largest savings potential and that also have not been examined through other studies. The Scope of Work for the RFP is being developed.

### New Construction Standard Practice - CT

This CT study is expected to examine how builders typically incorporate efficiency measures in residential buildings constructed both within and outside of Energy Star program activities.  The first phase of the study is expected to incorporate surveys and interviews with builders and contractors to examine current building practice.  Site visits will be used to verify reported building practices.  A second phase will look more closely at program processes and participation.  A Scope of Work is currently under development.

#### eeSmarts Evaluation - CT

The draft decision in Docket No. 07-10-03 denied a motion by UI to use teachers’ assessments of their training programs and materials in lieu of a formal evaluation.  Therefore, a formal follow-up evaluation has been initiated.  That evaluation will assess the progress made since implementation of the 2006 Process Evaluation.  Goodman Research Group has been retained to complete the study.  A final report is due by mid-October.

### Commercial/Industrial Studies

#### ISO M&V Requirements - Complete

### Small Business Energy Advantage Impact Evaluation - CT

The impact evaluation of the SBEA program will determine coincidence factors, energy and demand savings, realization rates and hours of use for prescriptive measures installed through the SBEA Program. The evaluation will involve on-site metering using data loggers, lighting loggers and hand held fixture Wattage measurement devices.

The Cadmus Group was selected to conduct this study.  Project kick-off was on August 29th.  So far Cadmus has produced a workplan based on the kickoff and has begun collecting program data.

The final report is expected by the end of January 2009.

### C&I Spillover and Free-Ridership Study - Regional

The Regional Group led by NGRID initiated a study to assess free-rider and spillover factors for the energy efficiency measures and programs offered to the Sponsors’ commercial and industrial customers.    PA Consulting was selected to complete the project on January 16th and began immediately.  Preliminary results and a draft report are available for both  UI programs and CL&P programs.  The study will be complete by the end of the summer of 2008.

#### C&I HVAC Peak Impacts - Unitary HVAC - Regional

#### Study delayed to 2009 summer season.  Scheduled to be part of the EM&V Forum.

#### Omnibus Load Shape Study - Regional

This regional study will require a contractor to collect load shapes developed at other utilities for measures offered in New England.  The contractor will assess whether or not the load shapes reflect situations sufficiently comparable to those in New England to enable us to use them in filings when utility-specific information is not yet available.  NEEP has volunteered to lead this study.  It is currently scheduled to be part of the EM&V Forum.

#### C&I Measure Persistence of Savings - Regional

Tentatively planned for late 2008 (or early 2009), this regional study will examine persistence of savings for measures installed under C&I programs.  Among the issues to be addressed is the question of how changes in business within a given location affect measure persistence and whether such changes as may be found should result in changes in participant targeting or eligibility.  The EM&V Forum is expected to start this project in 2009.

#### Market Opportunities Studies – delayed to 2009

### Maximum Potential Study - CT

A Maximum Achievable Potential study was ordered by the State Legislature in 2007.  KEMA was selected as contractor for the study on March 19.  Work on the project began immediately following the kick-off meeting on March 28.  During June, the gas utilities’ efficiency potential study was added to the scope of work for this project.

Much of the month was spent determining what measures and applications are to be included in modeling for gas and electric efficiency potential.  KEMA believes it is on schedule to complete the electric study at the end of September.  The gas study will be completed soon thereafter.

### EM&V Forum

The EM&V Forum has initiated funding and organization issues.  A meeting is scheduled for September 26 to develop plans for 2009.  The agenda shows (email from Julie Michals dated September 8, 2008):

This meeting is for all project committee and subcommittee members, the purpose of which is to discuss and finalize recommendations for the Forum’s Steering Committee consideration on October 10 regarding the Forum’s 2008-09 agenda and budget.  Prior to the Sept 26 meeting, we will send draft project recommendations prepared by each project subcommittee for your review.  You can view subcommittee conference call notes at http://www.neep.org/policy_and_outreach/EMVcalendar.html#subcommittee .  Please RSVP regarding whether you plan to participate in this meeting, and if so whether in person or by phone.   Thanks!

Meanwhile, a couple heads up on some Forum and other M&V developments:

1)  EM&V Protocol/Methods project – I will be sending out this week a short survey to representatives from each state requesting they prioritize on which EM&V elements (e.g., calc methods, baseline, data collection, etc.) the Forum should focus this project for protocol development given their current state priorities, and will request a quick turn-around on responses.  The results of the survey will inform the draft recommendation/project scope to be prepared by the project subcommittee.

2)  NAESB M&V protocol update - While the Forum is focusing on protocol development for electric and natural gas efficiency at this time, at the national level, the North American Energy Standards Board (NAESB) is developing draft M&V standards for wholesale demand response programs.  The first set of draft standards are to be released and reviewed at NAESB’s next meeting on October 3.  For more information about the NAESB project and upcoming meeting, go to http://www.naesb.org/dsm-ee.asp .  There is also a separate but related effort by NAESB to develop retail demand response M&V protocols, largely to assist regions of the country without ISO/RTO wholesale programs.

The ECMB Board needs to consider how it wants to interact and participate in the Forum.  I suggest adding this issue to the agenda of the next meeting.